Sabbatical Plan Outline for Ray Director of Client Services at OCRCC:

Introduction

Purpose of the sabbatical: To recharge, pursue professional development through a holistic survivor yoga retreat, medical needs, and enhance leadership skills.

Duration and timing: October 17th- November 27th. This timeframe is chosen to minimize disruption to OCRCC operations and ensure a smooth transition.

Preparation Phase

Responsibility: Director of Client Services

- Contract Management: Ensure all contractors receive, sign, and return their contracts, and that completed contracts are delivered to Laing as well as instructions on who to contact while out.

- Scheduling: Plan and finalize the six-week schedule, including group meetings, Healing Together events, and OVW events. Ensure all these events are accurately reflected in the shared calendar.

- Time Off and Scheduling: Update time-off requests and schedules in both the CST schedule and individual calendars to maintain clarity and coverage.

- Clients: The three clients I have will have all contact information and a match with an advocate if they need to access someone while I am out.

Delegation responsibilities:  interim leadership duties

  - Imani

    - Holding CST meetings WEEKLY creating and maintaining supervision notes in: 2024 Supervision

    - Providing ED with CST updates which can be found here as well: 2024 Supervision

    - Offer debriefing space for staff and interns as needed.

    - Maintain relationships with hospital staff and UNC schools.

    - Oversee and support helpline volunteers.

    - Supervise Tiny for an additional 30 minutes per week.

  - Rationale: Ensures continuity in leadership and support for client services, maintaining effective operations and staff engagement.

  - Tiny

    - Manage all group emails, redirecting them as necessary.

    - Handle contracts and invoice documentation related to therapists.

    - Support interns in therapy and support group programs.

    - Address Support group and therapy program needs as they arise.

    - Provide 30-minute debriefing sessions after the first and last support group sessions, as needed.

    - Supervise and support volunteers for the SGF role.

  - Rationale: Ensures smooth management of administrative tasks and program support, addressing any immediate needs.

  - Leah

    - Providing interns group supervision for 6 weeks tapping briana when needed.

    - Meet with students and professors as needed.

    - Complete any paperwork related to internships as needed

    - Complete or support in the completion of intern interviews.

  - Rationale: Maintains the quality of intern supervision and supports ongoing administrative tasks.

  - Briana will maintain and support me through:

    - Supporting Leah with group supervision when needed to make sure supervision is still happening while I am away.

    - Interviewing and obtaining intern applications and delegating to each department as needed.

  - Rachel and Laing will maintain and support me through:

    - Supervising either:

      - Supervise either Imani 1:1 or Leah, Osney, and Alexandria 1:1.

      - Manage any project oversite

      - Changes to wait till Ray gets back

Email will be set with a similar signature as when I am out for 2 weeks. All invoices will be sent directly to Rachel and Laing (sometimes Tiny) instead of me. Project oversight will be ensured by Rachel and Laing as a team.